## CHNA_ImplPlan_2020-22
CHNA Implementation Plan Tactics - Henry & Benton Counties MO
Wave #3 2019 CHNA Health Needs Tactics - Year 1 of 3 (Starting 1/1/2020 ) Updated: April, 2022
| CHNA Health Areas of Need | T | "Specific Actions" to Address Community Health Need or "Reasons Why Hospital Will Not" Address Need | Identified "Lead" | Identified Partners | Timeframe | GVMH Funding | Compass Funding | HCHC Funding | City of Clinton Funding | Schools Funding | Other Funding $$ | TOTAL | NOTES
1 | Mental Health School focused (Diagnosis, Treatment, Aftercare) / Suicides | a | Continue to build community BH education program. Collaborate with community elementary, middle, and high schools to educate students on mental health (de-stigmatize mental health conditions, suicide prevention and social media bullying). | Compass / Schools | GVMH, Law Enf, MO, Cities, Counties, Colleges, HCHC, Kaysinger Basin, MU Ext, WCCAA | 01/01/20 - 12/31/20 |  | 33346 |  |  |  |  | 33346 | Second Quarter 2021 - Compass has an MOU with both Clinton head start and Calhoun to provide assessment, training teachers on interventions in the classroom. Compass provides mental health groups for children ages 6-18 on different subjects ranging from Anger Management to mental health stigma. School campus assessments are provided during crisis when requested or needed. Compass has a School-Based Therapist working full-time remote to serve the needs of the Clinton school district. Goal Achieved, Second Quarter 2021
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Maintain a Community Inventory of Services to document the availability of mental health resources, including hours of service. Make BH Inventory available to the public as needed. Document mental health services by age categories. |  |  |  |  | 1400000 |  |  |  |  | 1400000 | Fourth Quarter 2020 Compass Health Website updated and lists available mental health resources by county and age category. Hours of service are listed on the website. https://compasshealthnetwork.org/services/behavioral-health/ Goal Achieved. Fourth Quarter 2020.
|  | c | Continue Mental Health care support at clinics. Increase depression screenings by PCPs. Add trauma assessment for pediatrics and other MH issues. | [9 empty] | 0 | Fourth Quarter 2020 The PHQ9, PHQ2 Depression Screens are completed during clinic visits. The Columbia Suicide Risk Assessment protocol implemented through various Compass Health Programs. Goal Achieved. Fourth Quarter 2020.
| Mental Health School focused (Diagnosis, Treatment, Aftercare) / Suicides | d | Investigate grant writing to fund mental health education and services. If available, designate community lead to attain the necessary grant. | [9 empty] | 0 | Third Quarter 2021- Benton County Youth Colaition received the Mega Grant for FY22. It is the DMH Mega Grant in the amount of $100,000 per year for 2 fiscal years. It includes a $55,000/year salaried FTE and the rest to implement an evidence-based program into the county. BCYC chose the "Too Good for Drugs and Violence (TGDV)" program. Fourth Quarter 2021-No New updates First Quarter 2022- No New updates
|  | e | Partner to improve mental health service "first aid" training for law enforcement, schools, and other first responders in the community. | Compass |  | 01/01/20 - 12/31/20 |  | 9129 |  |  |  |  | 9129 | Third Quarter 2021- Virtual trainings have been scheduled due to COVID concerns with meeting in person. Prevention is the Lead on this training. The Henry County Health department scheduled trainings but canceled due to low participation. There is a new staff that has taken the lead and will be coordinating trainings with the Health department. Fourth Quarter 2021-No New Updates First Quarter 2022 - No New Updates
|  | f | Continue Suicide prevention training at schools. Develop and sponsor an anti-suicide campaign for local community members. (Schools= $500 per kit each year) | Compass / Schools |  | 01/01/20 - 12/31/20 |  | 4547 |  |  | 500 |  | 5047 | Third Quarter 2021- Henry County provided training four years ago; Benton county is being coordinated by the coalition. Fourth Quarter 2021- No New Updates.
|  | g | Educate GVMH staff regarding mental health service delivery. Create updated brochures on mental health services. Continue ED tele psych service offerings. | GVMH |  | 01/01/20 - 12/31/20 | 50000 | [5 empty] | 50000 | Fourth Quarter: Complete for 2020, repeat in 2021. ROH and GVMH staff attends the monthly CIT Counsel and provides training. Program brochures were shared among the teams. In Progress for 2022.
|  | h | Continue to grow School Counselors (Compass partnership) in Clinton Schools. Expand into Warsaw and Clinton school districts. Recruit for Social Workers, Counselors and MH Providers in schools. | Schools/ Compass | [8 empty] | 0 | Third Quarter 2021-MOU signed with Benton and Henry County, Efforts have been made with lack of qualified applicants at this time in Warsaw. Fourth Quarter 2021- No New Updates First Quarter 2022- The search for qualified applicants continues.
|  | i | Continue to have Law Enforcement / Providers complete CIT training (20 hour training). | Law Enf / City |  | 2020 |  | 16413 |  | 3000 |  |  | 19413 | **City: Police time
|  | J | Encourage participation to attend monthly meetings (MissouriCIT.com). | [9 empty] | 0 | Fourth Quarter 2020 - Compass Health Staff attending monthly CIT Meetings. In progress for 2022.
|  | k | Continue with Compass Crisis training on school campus'. | Compass | [8 empty] | 0 | Third Quarter 2021-Lincoln School and Benton County reached out for de-escalation training. Compass has youth ERE. Fourth Quarter 2021-No New Updates.
|  | l | Continue with MU Ext Youth MH Course offerings. | MU Ext | [8 empty] | 0 | Fourth Quarter 2021- No new Updates. First Quarter 2022 - No new Updates
|  | m | Continue to offer and promote the QPR Compass Program for community members. | Compass |  | 01/01/20 - 12/31/20 |  | 4547 |  |  |  |  | 4547 | Third Quarter 2021 - Community CHNA Committee Formed in second quarter for recommendation to meet this objective. -- Pending
2 | Economic Development | a | Continue with Workforce Ready Community Assessment. Continue the PSA economic development advisory group to lead local efforts and actively recruit new businesses / retain existing businesses in the PSA. | Chamber (Clinton) / City of Warsaw | Cities, Kaysinger Basin, GVMH, MU Ext, Clergy, HCHC, Compass, MO, Providers, Royal Oaks, | [7 empty] | 0
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Continue to report PSA business retention and expansion data. Complete compliance checks for area businesses. | [9 empty] | 0
|  | c | Expand PSA Economic Development efforts to decrease poverty / increase access to health insurance. | [9 empty] | 0
|  | d | Encourage local businesses to host job fairs to promote their open positions for all education levels. (no degree, GED, etc.) | SFCC |  | 2020-03-01 | [5 empty] | 500 | 500 | TLF: All Companies in Benton and Henry Counties
|  | e | Continue to partner with Kaysinger Basin and understand their indicatives. Help further launch this support in Henry and Benton County. | SFCC |  | 2020-02-01 | [5 empty] | 100 | 100 | TLF: Warsaw, Bolecamp, Lincoln, Chambers, MU Ext
|  | f | Continue to provide labor information explaining skill level to recruit new businesses in County. Identify incentives to attract and retain. | City |  | 01/01/20 - 12/31/20 |  |  |  | 24000 |  |  | 24000 | **25% of City budget
|  | g | Create County Economic Dev Zone Credit / apply for community benefit grant to finance. | [9 empty] | 0
|  | h | Continue to promote small business growth by securing grants / endowment funds (banking). | [9 empty] | 0
|  | i | Continue to host employable skills training and career fairs with high school / college students. Build a program in partnership with the chamber, hospital, career center, Kaysinger and other PSA businesses. | City / GVMH / SFCC |  | 2020-06-01 | 3000 |  |  | 24000 |  | 250 | 27250 | **25% of City budget TLF: MO One Start, Ec Dec, SBDC Programs, Referrals, trainings in Clinton
|  | j | Continue with the Existing Business Program study with surveying to retain and grow small businesses. Utilize the job training funds. Launch this initiative in Benton Co. | City | [5 empty] | 48000 |  |  | 48000 | **50% of City budget
3 | Drugs (Opioids, Meth, Heroin, Marijuana) | a | Provide tobacco / drug / alcohol education to students (i.e. DARE, etc.) and increase school-based programs. Apply for grants. Work with the health education classes. | HCHC / Compass | Schools, Pharmacies, Providers, Law Enf, GVMH, Chambers, Cities, Counties, MO, Schools, Colleges, WCCAA | 01/01/20 - 12/31/20 |  | 4547 | 2000 | 1716 | 1590 | 7000 | 16853 | Third Quarter 2021- Benton County Youth Coalition have one grant awarded to them this fiscal year (FY22). It is the DMH Mega Grant in the amount of $100,000 per year for 2 fiscal years. It includes a $55,000/year salaried FTE and the rest to implement an evidence-based program into the county. BCYC chose the "Too Good for Drugs and Violence (TGDV)" program There is currently Adolescent C-Star programs in Henry and Benton Counties. Goal Achieved
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Research prevalent issues leading to drug abuse by adolescents. Continue to develop meaningful community youth activities which deter them from the research findings. | [5 empty] | 500 |  |  |  | 500 | Third Quarter 2021- Benton County Youth Coalition have one grant awarded to them this fiscal year (FY22). It is the DMH Mega Grant in the amount of $100,000 per year for 2 fiscal years. It includes a $55,000/year salaried FTE and the rest to implement an evidence-based program into the county. BCYC chose the "Too Good for Drugs and Violence (TGDV)" program The community coalition should be responsible for these efforts.- Goal Achieved
|  | c | Build Recovery support system partners. Create programs to help addicts and their families. Continue to provide counseling and support for drug abusers and their families. Support local substance abuse counseling. Educate public on signs of drug abuse and how to approach those needing guidance. | [8 empty] | 7000 | 7000 | Third Quarter 2021- Training will be provided in November 2021. CPRC staff have been trained on overdose treatment and will provide training to consumers. All clients can access same day services through open access from 8:00-4:00 Monday-Friday. - Goal Achieved
|  | d | Monitor prescription drug abuse. Support PSA providers in discouraging prescription drug abuse. Create an alert system between providers and pharmacies for drug abuse. | GVMH |  |  | 6000 |  | 1000 |  |  |  | 7000 | PDMP is being utilized in Henry and Benton County.
|  | e | Investigate grant writing to fund Drug Abuse education / counseling. If available, designate community lead to work to attain the necessary grant. | [9 empty] | 0 | Second Quarter 2021 - A SAMSHA Grant was awarded in May 2021. The 24-month grant includes Henry County. The purpose of this grant is to increase access to and improve the quality of community mental health and substance use disorder treatment services through the expansion of CCBHC programming. Compass is also providing 24/7 crisis intervention services for individuals with SMI, SUD, including opioid use disorders, SED, COD (grant runs through 4/30/22) . Compass received a contract the Dept of Mental Health for the State Opioid Response grant that covers and supports services for Henry County residents. The contract runs through Sept 29, 2021. Goal Achieved Second Quarter 2021
|  | f | Promote discarding old prescriptions (Prescription take-backs) at local police departments, especially opioids. | City / Law Enf | [5 empty] | 500 |  |  | 500 | **Clinton Police Dept time
|  | g | Continue to develop pain management programs. Meet with partners to assess the current needs and initiatives. Continue to educate providers on alternative pain control resources. | [9 empty] | 0
|  | h | Continue to promote Recovery Court in PSA Clinics. Expand this service to Benton County. | [6 empty] | 3250 |  |  | 3250 | **Clinton Police Dept time
|  | i | Continue to improve access to suboxone treatment services. |  |  | 01/01/20 - 12/31/20 |  | 427974 |  |  |  |  | 427974 | **2021 Grant HCHC
|  | j | Continue to utilize HCHC grant $$/funding to set programs up in schools in PSA. |  |  | 2021 |  |  | 4000 |  |  |  | 4000 | **2021 Grant HCHC
|  | k | Expand screening brief intervention referral and treatment (SBIRT). Promote evidence-based interventions. | [9 empty] | 0
4 | Lack of Inpatient Psychiatric beds | a | Implement ERE Program at GVMH to benefit residents in the PSA. | Compass / GVMH | Law Enf (CIT), MO, Providers, Royal Oaks, | [7 empty] | 0 | Emergency Room Enhancement Expanded. A new protocol was developed for after-hours community assistance for patients with poor med adherence. Med Refill Nurses on call and coordinate with practitioners. . Goal Achieved Third Quarter 2020. Fourth Quarter 2020 - protocol continues to exist.
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Retain existing psychiatric providers and determine if additional providers should be recruited. | GVMH / Compass |  | 01/01/20 - 12/31/20 | 25000 | [5 empty] | 25000 | Fourth Quarter of 2020. An additional 10 hours of FMHNP mental health services are planned to be added in Benton County (Warsaw). There are currently eight outpatient psychiatric providers between Henry & Benton County. Royal Oaks Hospital has one full-time FMHNP, four full-time psychiatrists, and covering providers. Beginning January 2020 Dr. Sethi, psychiatrist plans to provide three additional days of coverage. Action Plan Achieved. Continue to monitor for 2021. Action Plan Achieved. Continue to monitor for 2022.
|  | c | Continue to recruit providers to area. Utilize national recruiters to find quality providers. | GVMH / Compass |  | 01/01/20 - 12/31/20 | 10000 | [5 empty] | 10000 | Fourth Quarter of 2020. Ten hours of PMHNP services were added to Benton County (Warsaw). Action Plan Achieved. Continue to monitor for 2022.
|  | d | Expand Inpatient Adult / Geriatric Behavioral services. | Compass | [8 empty] | 0 | New ROH Adult Unit expanded from 6-14 beds. Goal Achieved Third Quarter 2020.
|  | e | Continue to promote Royal Oaks Hospital (54+ beds) in Windsor. Utilize their services within both counties. | Compass | [8 empty] | 0 | Fourth Quarter of 2020. Community Referrals System enhanced with GVMH Emergency Room. Additional service enhancement by reviewing patient's needed services for discharge and coordinating a discharge plan. Goal Achieved Third Quarter 2020.
|  | f | Continue to seek MO grant to help fund the Diversion center. | Compass | [8 empty] | 0 | Third Quarter 2021- Benton county received the mega grant. Compass applied for the CCBHC grant. This will aid in the new Crisis Center in Raymore. We will get results in September 2021. There is a new hosptial access liason working in Golden Valley Hospital that aids individuals not meeting criteria for ERE. They can help access resources. There is ERE in Henry County. Goal Achieved
|  | g | Explore WCCAA partners for transitional (Step Down) housing (MO Dept of MH). | WCMCAA | [8 empty] | 0
|  | h | Launch Crisis Intervention Training classes to help community members / Providers and Law Enforcement secure their certification. | Law Enf / City | [8 empty] | 0
5 | Obesity (Nutrition / Exercise) / Food Insecurity | a | Collaborate with health plans, local cities and other groups focused on fitness, healthy eating, and access to fresh fruits and vegetables. | HCHC / MU Ext | WCCAA, Harvesters, GVMH, Schools, Colleges, Cities, Counties, Clergy, Chambers, Kaysinger Basin, WIC, Fitness Centers, Compass, 4H Clubs, Samaritan Center | [7 empty] | 0 | 2021 - Pending Board Approval of Budget (HCHC)
|  | b | Grow & promote community farmer's market. Offer gardening classes. Support “Farm to School” program to provide local produce to students. | WCMCAA | [7 empty] | 15000 | 15000
|  | c | Expand free cooking classes to community. Create & publish health low cost recipe book outlining healthy dinners and/or Dining with diabetes/food restrictions. | MU Ext |  |  |  |  | 2000 |  |  |  | 2000
|  | d | Create and promote a community garden where locals can grown and produce their own food to decrease meal costs and increase healthy eating. | [9 empty] | 0
|  | e | Develop support for local food bank and/or other food giveaway options. | [9 empty] | 0
|  | f | Educate & expand youth physical activity programs. Create after school programs to keep youth active. | Samaritan Center |  |  |  |  | 1500 | 304662 |  | 60000 | 366162 | **25% of City P&R Budget
|  | g | Establish relationship with schools to provide education to students and families about health eating strategies. Encourage health after school snacking. | Schools / MU Ext |  |  |  |  | 550 |  |  |  | 550
|  | h | Continue to promote community health. Create effective media (i.e. print, radio, digital). Continue to provide education to the community through health fairs and educational programs, including various screenings. | Compass |  |  |  |  | 3000 |  |  |  | 3000 | First Quarter 2022: Dental Radio Ads, flyers throughout communities, PSP events to give out information and referrals. Mobile Unit going to schools, Headstarts, and Nursing Homes to provide full dental care. PSP program to screen and give referrals, Attend Health Fairs, Back to School Fairs, Kindergarten Screenings, Go to Library’s with the toothfairy to read stories, Provide 3rd grade education program, provide nursing home program, provide adolescent program Compass is running about 500k streaming tv ads promoting mental, dental, and primary care. Compass is running radio advertising promoting all of our services. There are various print marketing in the community from school flyers, to chamber advertising, newspaper, etc. Compass has regular Facebook posts promoting services.
|  | i | Expand the Community Wellness Committee's (CWC) initiatives previously established and help implement the strategy. | ALL | [8 empty] | 0
|  | j | Continue the wellness incentive for GVMH, HCHC and Compass employees and launch "staff health" challenge. Continue to offer healthy food options on campus. | ALL |  |  |  | 110000 | 450 | 3182 |  |  | 113632 | **City program
|  | k | Continue with Nutritional Education classes (MU Ext), Nutrition Services (OP GVMH), and IP Compass services. | ALL | [8 empty] | 0
|  | l | Continue the "Commit to Fit" community-wide fitness challenge initiative focusing on fitness, nutrition and physical activity. | ALL |  | 01/01/20 - 12/31/20 | 2000 |  | 800 |  |  |  | 2800
|  | m | Continue to promote WIC and food stamp programs. Continue with School Back-pack program. Expand "No Kid Hungry" initiative in Clinton Schools. Expand program into Benton County. | Samaritan Center |  |  |  |  | 500 |  |  |  | 500
|  | n | Continue and encourage other schools to provide healthier options in school vending machines. | Schools | [8 empty] | 0
|  | o | Continue with Henry County Home Program "Building Community for Better Health Access to Healthy Foods" through the Community Coalition. Build "Girls on the Run" program. | HCHC |  | 01/01/20 - 12/31/20 ONLY |  |  | 1000 |  |  |  | 1000
6 | Poor Health Insurance (Lack of Coverage) | a | Expand Marketplace enrollment assistance education. Help residents enroll into Medicaid / ACA insurance coverage. Utilize Compass' Outreach representative to help students sign up for Medicaid. | Compass / HCHC / GVMH | Chambers, Cities, Counties, WIC, MO, | 01/01/20 - 12/31/20 |  | 33346 | 500 |  |  |  | 33846 | Third Quarter 2021 Update In progress with Compass Financial Assistance. Fourth Quarter 2021- Signs have been posted in lobbies with contact information to the Marketplace. In SUD, the IHS staff are talking to clients about reapplying for Medicaid and helping new clients enroll in Medicaid.- Goal Achieved
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Start proactive MO Medicaid Pass campaign. Continue to host public meetings to educate community on health reform law's insurance coverage options. | HCHC 2021 |  | 01/01/20 -11/17/20 | [6 empty] | 0 | Proactive MO Medicaid Program started on FB and via Compass Goal Achieved Third Quarter 2020.
|  | c | Partnering with surrounding hospitals to advocate for Medicaid Expansion. Mobilize hard to reach populations. | ALL |  | 01/01/20 -11/17/20 |  |  | 1700 |  |  |  | 1700 | Medicaid Expansion Campaign started throughout Compass using various social networking ie Facebook, Company Email. Mo Med Expansion passed August 2020.Goal Achieved Third Quarter 2020.
|  | d | Provide education class to public and community in regards to how to properly navigate the using your health insurance coverage properly. | ALL | [8 empty] | 0
|  | e | Continue to offer informative meetings at GVMH and sliding scale options at Compass and GVMH. Provide payment assistance programs to persons who have health care needs | GVMH |  |  | 553000 | [5 empty] | 553000 | Exceeded commitment. Will repeat for 2021.
|  | f | Research federal assistant for health insurance policies for rural health organizations. Investigate Trump Community Insurance pools. | ALL | [8 empty] | 0
|  | g | Continue to offer and promote the Clinton Chamber's "group plan options." | Chamber (Clinton) | [7 empty] | 2500 | 2500
7 | Housing (Safe and Affordable) | a | Create a County Housing Development Plan that would address affordable safe housing for community residents. Complete Henry and Benton county-wide housing study. | Cities of Warsaw / Clinton | WCCAA, HCHC, Counties, Compass, GVMH, Chambers, Harvesters, Kaysinger Basin, MU Ext, Schools, Colleges |  |  | 54000 |  |  |  | 14304 | 68304 | ** Annual Dev Budget - WCMCAA, Henry Co
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Explore and create a Habitat for Humanity-type process in Henry and Benton county area. | ALL | [8 empty] | 0
|  | c | Develop policies that set standards for rental properties and maintaining housing in PSA. Explore the set up of safe rental inspections. Utilize "Weatherization" with WCMCAA. | WCMCAA (2 Co) | [7 empty] | 80000 | 80000
|  | d | Investigate grant writing to fund public / safe housing. If available, designate community lead to work to attain the necessary grant. | Nap Grant | [7 empty] | 20000 | 20000
|  | e | Target infill development of existing infrastructures to encourage affordable home ownership. | WCMCAA (2 Co) | [7 empty] | 792408 | 792408 | **Multi-Family Housing Annual Budget - WCMCAA, Henry Co and Benton Co
8 | Transportation | a | Continue to research current transportation resources and gaps. Expand search to non-motorized transportation options. | WCCAA | Compass, GVMH, HCHC, MO, Cities, Law Enf (CIT), Counties, Schools, Colleges, | [7 empty] | 0
| This health need is not part of hospital mission of critical operations. Will partner with others as appropriate. | b | Develop and publish Henry / Benton Counties Transportation Master Plan. Track results annually. | [9 empty] | 0
|  | c | Communicate to the public what transportation services are available through mass media, online, digital, and at businesses in 2 counties. | [9 empty] | 0
|  | d | Explore transportation grants for Henry and Benton County. |  |  |  |  | 90000 |  | 69163 |  |  | 159163 | **City MODOT grant Goal Achieved 2020
|  | e | Identify home-based monitoring programs for health care service offerings. Encourage local payors to cover the monitoring. |  |  | 04/01/20 - 12/31/20 | 15000 |  |  |  |  | 10000 | 25000 | Software has been purchased and staff being trained for roll out.
|  | f | Continue to utilize OATS, ALS - City, HealthTran, Compass services, Dental Bus and others. |  |  | 01/01/20 - 12/31/20 | 41600 | 200000 |  | 69163 |  |  | 310763 | Program Initiated: **City share - Goal Achieved 2020
|  |  | Total Annual Contributions |  |  |  | 705600 | 2387849 | 19500 | 550636 | 2090 | 1009062 | 4674737
**Please Note: Compass Health Network funding is as follows: 1) Outreach and Enrollment $22,693 split (.5 FTE) for 1a $11,346 and 6a $11,346 plus $22,000; 2) MAT Dr Time $194,610 (.5 FTE) plus $174,364 (.5 FTE) for 3i plus $59,000; 3) Prevention Time $14,941 (.3 FTE) plus $3,249 (.08 FTE) total ($18,190) split by 1e ($4,547), 1f ($4,547), 1m ($4,547) and 3a ($4,547); 4) CMHL total $16,413 (.25 FTE) for 1i; and 5) Mental Health First Aid time $2,291 (.05 FTE) for 1e plus $6,838.

## StakeholdersKEY_Emails
Henry & Benton Co, Missouri Stakeholders
KEY | Name | Contact | Email
4H Clubs | 4H Clubs - local (Henry Co through MU Ext.) | Henry County 4-H Council officers: Co-Presidents -- Brendon Engeman and Jessalyn Caple (MU Ext- Susan Jones-Hard) | Mu Ext email
Chambers | Clinton Chamber of Commerce or City of Warsaw | Mark Dawson- Ec Dev Director; Debby VanWinkle- Chamber Director Clinton; Warsaw Chamber | mark@clintonmo.com; debby@clintonmo.com; warsawchamber@outlook.com
Cities | Clinton, Warsaw | Clinton- Christina Maggi, Warsaw- Randy Pogue | cmaggi@cityofclintonmo.com; randy.pogue@welcometowarsaw.com
Clergy | Ministerial Alliance | Clinton UMC | office@clintonumc.net
Colleges | SFCC, UM, CM | Tammy Woirhaye - SFCC | twoirhaye@sfccmo.edu
Compass | Compass Health Network (Henry and Benton) | Donni Kuck, Saundra Overton, others | dkuck@compasshn.org; soverton@compasshn.org
Counties | Henry and Benton County, MO
Ec Dev | Economic Development - Clinton | Mark Dawson | mark@clintonmo.com
Fitness Centers | PSA Community Center
GVMH | Golden Valley Memorial Healthcare | Craig Thompson, others | cthompson@gvmh.org
Harvesters | PSA Harvesters (26 Co area) | Sheila Barkwell- The Samaritan Center | The Samaritan Center email
HCHC | Henry County Health Center (including WIC) | Peggy Bowles, Kayla Meads, others | peggy.bowles@lpha.mo.gov
Kaysinger Basin | 7 Co (Bates, Benton, Cedar, Henry, Hickory, St Clair, and Vernon) (state initiative) Kaysinger Basin Regional Planning Commission | Ex Dir - Sheridan Garman-Neeman, Henry Co - Dale Lawler, Benton Co - Steve Daleske | sgarman@kaysinger.com
Law Enforcement | PSA City and Counties Law Enforcement (CIT training), Henry County Sheriff's office - Clinton | Chad Nepple - CPD, Rob Hills | c.nepple@clintonmopd.com; rob170k9@gmail.com
MO - State | State of Missouri
MU Ext | Missouri University Extention Office | Susan Jones-Hard | joneshards@missouri.edu
Pharmacies | PSA Pharmacies
Providers | PSA Providers of Healthcare
Royal Oaks | Royal Oaks Hospital (Compass) | Erin Allen, Erica Jenkins, others | ejenkins@compasshn.org
Samaritan Center | Samaritan Center - Clinton | Sheila Barkwell | director@clintonsamaritancenter.com
Schools | Clinton Schools, PSA schools | Teresa Howard (Social Work), Stacy Pitts, Michelle Henzlik- Clinton Intermediate, Angie Lawson, Jamie McCoy- Clinton HS Counselor, Makenna HixSherri Swope (Principal) | thoward@clintoncardinals.org; spitts@clintoncardinals.org; mhenzlik@clintoncardinals.org; alawson@clintoncardinals.org; jamccoy@clintoncardinals.org; mhix@clintoncardinals.org
WCCAA | West Central Missouri Community Action Agency | Kristina Klass, Linda Schreck, Patty Cantrell - New Growth, Kelly Ast | kklass@wcmcaa.org; lschreck@wcmcaa.org; pcantrell@newgrowthmo.org; Kast@wcmcaa.org